## Sheet1
Timeline | Activity | Task Identification | Owner | Target Date | Status
September - 1st SAC board meeting | Post basketball tournament dates/info | Post in Forum, Grand Forks Herald, Fargo Basketball Academy website; if possible email team coordinators from last year's teams the registration form | Athletic Director
2 months before | Create Volunteer site | Volunteer site for snacks/gate/concessions | SAC tournament coordinator
volunteer site for clock and book
6 weeks before | Email Volunteer site to McManus or Hughes family | November boys’ tournament-Mary McManus (ndmary3@cableone.net) | SAC tournament coordinator
February girls’ tournament-Sharon Hughes (shughes@catholiccharitiesnd.org 701.371.3366)
4 weeks before | Notify Elementary Schools | Put tournament info and volunteer site for snacks/gate/concessions in weekly newsletter at all 3 elementaries and at Sullivan | SAC tournament coordinator
| Notify Basketball coaches | Ask Varsity/JV coaches to encourage players to fill clock/block spots using Sign Up.com link | SAC tournament coordinator
2 weeks before | monitor Volunteer spots available | Review and ensure spots are getting filled for both Sign up.com sites (snack/gate/concessions and clock/book) | SAC tournament coordinator
1 week before | Key to building | If AD or Asst. AD will not be at tournament, work with Stacey Roney to fill out paperwork to get master key | SAC tournament coordinator
Day of Tournament | pick up snacks from Elementary schools | All snacks will be transported to Shanley concessions area | SAC tournament coordinator
| Setup gyms | Arrive early to set up chairs and clock/book table | SAC tournament coordinator & AD
| Oversee tournament | Ensure Refs get food/drinks between games | SAC tournament coordinator
Monitor restrooms cleanliness & empty trash
check/empty big trash bins in gyms periodly
| Clean Concession | scrub and sanitize concessions area | SAC tournament coordinator